WP3 11.02.22

---
Tasks done during the week
- Rewrote clustering script
  - Runtime: 12h → 20 min
- Ran snakemake pipeline with right lobe of liver data
  - Diabled plotting for runtime: 3d → 1d
- Attempted proper hierarchical clustering for TF families
- Adapted scripts to new data
- Wrote script to compare TF profile similarity

---
Workflow
All.bam
Clustering.py
TOBIAS
ATACorrect
TOBIAS
ScoreBigwig
TOBIAS
BINDetect
Cluster1.bam
Cluster2.bam
Etc.
Cell
Assignment
Table
TF_families.py
     Bindetect
   _distances.txt
Of different runs
Profile
Similarity.py
ImportantTFs
PerCluser.tsv
DefiningTF.py
Compare
Cluster
Score.py
ClusterComparison
.tsv
bindetect_results.txt
Biological
Implications?
Wilson
Heatmap
Visualisation

---
Wilson Heatmap
Defining Transcription Factors

---
Overlapping Defining Transcription Factors between clusters

---
Biological Questions / Goals of Analysis
- How does the transcription factor profile correspond to cell type?
- Do similar cell types in different tissues also have a similar TF profile?
  - Can cell type assignment be verified by this?
  - Usable to predict unknown cell types?

---
Problems
- Have not been able to convert hierarchical clustering to TF families
- Used Scipy

---
ToDos
- Fix TF families with hierarcical clustering
- Improve visualisation (Profile Similarity)
- Naming the clusters
  - Requires names from WP1/2
  - tsv with # and cell type should already work with clustering script
- Clean up code and documentation